## READ ME
BLACK VOYAGE — Flow Master Sheet · updated to Workflow v2
Pre-filled from BV Team Workflow_v2.pdf + the live tracker. YELLOW = fill/confirm · BLUE = NEW in v2 (please verify these first).
Tab 1 · Projects | Active launches with DRI, stage, target.
Tab 2 · Tasks | Full task list per project incl. all NEW v2 tasks (blue): Marketing brief rough draft, department requirements, dispatch & tracking, Shipbob / Next Smart Ship SKUs, All-ASINs & COGS sheets, shipping labels, inventory receiving, content export now incl. Ads.
Tab 3 · People | Fill heads / members / deputies per department.
Tab 4 · Push rules | Stage transitions updated to v2 exit criteria — Logistics & Marketing now gate Production; Catalog gate grew to 10 items.
Tab 5 · Contingencies | Trigger → fallback plans; new Shipbob/3PL row added.
Tab 6 · Rules | Operating rules with Confirm Y/N.
YELLOW = needs input | BLUE = NEW in Workflow v2

## 1. Projects
PROJECTS
Project | DRI (department) | Current stage | Target launch | Health | Key links | Notes
Vesper | Product | Concept | 2026-12-04 | Fresh card — intake form not yet filled
Apex | Product | Build | 2026-08-12 | Waiting on Ben validation ◆
Cyclone | Content | Content | 2026-09-30 | Blocked: A+ assets (font license)
Zephyr | Marketing | Complete | 2026-04-15 | Launched — reference

## 2. Tasks
TASKS — per project (v2 task set; BLUE rows = new in v2)
Project | Stage | Department | Task | Status | Assignee | Due | Urgency | Evidence req. | Link | Notes
Vesper | Concept | Product | Form (intake) | To do |  |  | med | No | docs.google.com/…/intake-vesper
Vesper | Concept | Product | Market research | To do |  |  | med | No
Vesper | Concept | Product | Concept definition | To do |  |  | med | No
Vesper | Concept | Product | Ben concept sign-off ◆ | To do |  |  | high | No
Vesper | Build | Product | Prototype 1-2-3 approved | To do |  |  | med | Yes
Vesper | Build | Product | Ben validation ◆ | To do |  |  | high | No
Vesper | Build | Product | Costing & profit signed off | To do |  |  | med | No
Vesper | Build | Design | Packaging / insert / manual locked | To do |  |  | med | No
Vesper | Build | Design | Model name set | To do |  |  | med | No
Vesper | Production | Product | Design freeze | To do |  |  | med | No
Vesper | Production | Marketing | Marketing brief rough draft | To do |  |  | med | No |  | NEW in v2
Vesper | Production | Product | Department requirements collected | To do |  |  | med | No |  | NEW in v2
Vesper | Production | Product | Pre-production sample approved + BOM | To do |  |  | med | Yes
Vesper | Production | Product | Mass production complete | To do |  |  | med | Yes
Vesper | Production | Logistics | Dispatch details & tracking filed | To do |  |  | med | No |  | NEW in v2
Vesper | Production | Logistics | Freight booked (sea + air samples) | To do |  |  | med | No
Vesper | Content | Content | Hero / lifestyle shoot done | To do |  |  | med | Yes
Vesper | Content | Content | Post-production done | To do |  |  | med | No
Vesper | Content | Content | Content exported (instr/lifestyle/social/ads) | To do |  |  | med | Yes
Vesper | Content | Design | A+ / infographic assets ready | To do |  |  | med | Yes
Vesper | Listing creation | Catalog | Amazon SKU created | To do |  |  | med | Yes
Vesper | Listing creation | Catalog | Shopify SKU created | To do |  |  | med | Yes
Vesper | Listing creation | Catalog | Shipbob SKU created | To do |  |  | med | Yes |  | NEW in v2
Vesper | Listing creation | Catalog | Next Smart Ship SKU created | To do |  |  | med | Yes |  | NEW in v2
Vesper | Listing creation | Catalog | All ASINs sheet updated | To do |  |  | med | Yes |  | NEW in v2
Vesper | Listing creation | Catalog | Shopify COGS sheet updated | To do |  |  | med | Yes |  | NEW in v2
Vesper | Listing creation | Logistics | Shipping labels created (Amazon + Shipbob) | To do |  |  | med | Yes |  | NEW in v2
Vesper | Listing creation | Catalog | Product data filed → marketing brief | To do |  |  | med | No
Vesper | Listing creation | Catalog | Brand language confirmed ◆ | To do |  |  | high | No
Vesper | Listing creation | Design | Listing imagery / A+ uploaded | To do |  |  | med | No
Vesper | Live | Catalog | Listings published live (Amazon + Shopify) | To do |  |  | med | Yes
Vesper | Live | Logistics | Inventory received (Amazon + Shipbob) | To do |  |  | med | No |  | NEW in v2
Vesper | Live | Marketing | Marketing brief finalized & ready | To do |  |  | med | Yes
Vesper | Marketing | Marketing | KOL / influencer projects live | To do |  |  | med | No
Vesper | Marketing | Social | Channel posts live (IG/YouTube/TikTok) | To do |  |  | med | No
Vesper | Marketing | Ads | Launch ads running | To do |  |  | med | Yes
Vesper | Marketing | Email | Launch email sequence sent | To do |  |  | med | No
Apex | Concept | Product | Form (intake) | Done |  |  | med | No
Apex | Concept | Product | Market research | Done |  |  | med | No
Apex | Concept | Product | Concept definition | Done |  |  | med | No
Apex | Concept | Product | Ben concept sign-off ◆ | Done |  |  | urgent | No
Apex | Build | Product | Prototype 1-2-3 approved | Done |  |  | med | Yes | drive.google.com/…/apex-qc
Apex | Build | Product | Ben validation ◆ | Waiting on Ben ◆ |  |  | urgent | No
Apex | Build | Product | Costing & profit signed off | Done |  |  | med | No
Apex | Build | Design | Packaging / insert / manual locked | Done |  |  | med | No | drive.google.com/…/apex-packaging
Apex | Build | Design | Model name set | Done |  |  | med | No
Apex | Production | Product | Design freeze | To do |  |  | med | No
Apex | Production | Marketing | Marketing brief rough draft | To do |  |  | med | No |  | NEW in v2
Apex | Production | Product | Department requirements collected | To do |  |  | med | No |  | NEW in v2
Apex | Production | Product | Pre-production sample approved + BOM | To do |  |  | med | Yes
Apex | Production | Product | Mass production complete | To do |  |  | med | Yes
Apex | Production | Logistics | Dispatch details & tracking filed | To do |  |  | med | No |  | NEW in v2
Apex | Production | Logistics | Freight booked (sea + air samples) | To do |  |  | med | No
Apex | Content | Content | Hero / lifestyle shoot done | To do |  |  | med | Yes
Apex | Content | Content | Post-production done | To do |  |  | med | No
Apex | Content | Content | Content exported (instr/lifestyle/social/ads) | To do |  |  | med | Yes
Apex | Content | Design | A+ / infographic assets ready | To do |  |  | med | Yes
Apex | Listing creation | Catalog | Amazon SKU created | To do |  |  | med | Yes
Apex | Listing creation | Catalog | Shopify SKU created | To do |  |  | med | Yes
Apex | Listing creation | Catalog | Shipbob SKU created | To do |  |  | med | Yes |  | NEW in v2
Apex | Listing creation | Catalog | Next Smart Ship SKU created | To do |  |  | med | Yes |  | NEW in v2
Apex | Listing creation | Catalog | All ASINs sheet updated | To do |  |  | med | Yes |  | NEW in v2
Apex | Listing creation | Catalog | Shopify COGS sheet updated | To do |  |  | med | Yes |  | NEW in v2
Apex | Listing creation | Logistics | Shipping labels created (Amazon + Shipbob) | To do |  |  | med | Yes |  | NEW in v2
Apex | Listing creation | Catalog | Product data filed → marketing brief | To do |  |  | med | No
Apex | Listing creation | Catalog | Brand language confirmed ◆ | To do |  |  | urgent | No
Apex | Listing creation | Design | Listing imagery / A+ uploaded | To do |  |  | med | No
Apex | Live | Catalog | Listings published live (Amazon + Shopify) | To do |  |  | med | Yes
Apex | Live | Logistics | Inventory received (Amazon + Shipbob) | To do |  |  | med | No |  | NEW in v2
Apex | Live | Marketing | Marketing brief finalized & ready | To do |  |  | med | Yes
Apex | Marketing | Marketing | KOL / influencer projects live | To do |  |  | med | No
Apex | Marketing | Social | Channel posts live (IG/YouTube/TikTok) | To do |  |  | med | No
Apex | Marketing | Ads | Launch ads running | To do |  |  | med | Yes
Apex | Marketing | Email | Launch email sequence sent | To do |  |  | med | No
Cyclone | Concept | Product | Form (intake) | Done |  |  | med | No
Cyclone | Concept | Product | Market research | Done |  |  | med | No
Cyclone | Concept | Product | Concept definition | Done |  |  | med | No
Cyclone | Concept | Product | Ben concept sign-off ◆ | Done |  |  | high | No
Cyclone | Build | Product | Prototype 1-2-3 approved | Done |  |  | med | Yes
Cyclone | Build | Product | Ben validation ◆ | Done |  |  | high | No
Cyclone | Build | Product | Costing & profit signed off | Done |  |  | med | No
Cyclone | Build | Design | Packaging / insert / manual locked | Done |  |  | med | No
Cyclone | Build | Design | Model name set | Done |  |  | med | No
Cyclone | Production | Product | Design freeze | Done |  |  | med | No
Cyclone | Production | Marketing | Marketing brief rough draft | Done |  |  | med | No |  | NEW in v2
Cyclone | Production | Product | Department requirements collected | Done |  |  | med | No |  | NEW in v2
Cyclone | Production | Product | Pre-production sample approved + BOM | Done |  |  | med | Yes
Cyclone | Production | Product | Mass production complete | Done |  |  | med | Yes
Cyclone | Production | Logistics | Dispatch details & tracking filed | Done |  |  | med | No |  | NEW in v2
Cyclone | Production | Logistics | Freight booked (sea + air samples) | Done |  |  | med | No
Cyclone | Content | Content | Hero / lifestyle shoot done | Done |  |  | med | Yes | drive.google.com/…/cyclone-shoot
Cyclone | Content | Content | Post-production done | In progress |  |  | med | No
Cyclone | Content | Content | Content exported (instr/lifestyle/social/ads) | To do |  |  | med | Yes
Cyclone | Content | Design | A+ / infographic assets ready | Blocked |  |  | med | Yes
Cyclone | Listing creation | Catalog | Amazon SKU created | To do |  |  | med | Yes
Cyclone | Listing creation | Catalog | Shopify SKU created | To do |  |  | med | Yes
Cyclone | Listing creation | Catalog | Shipbob SKU created | To do |  |  | med | Yes |  | NEW in v2
Cyclone | Listing creation | Catalog | Next Smart Ship SKU created | To do |  |  | med | Yes |  | NEW in v2
Cyclone | Listing creation | Catalog | All ASINs sheet updated | To do |  |  | med | Yes |  | NEW in v2
Cyclone | Listing creation | Catalog | Shopify COGS sheet updated | To do |  |  | med | Yes |  | NEW in v2
Cyclone | Listing creation | Logistics | Shipping labels created (Amazon + Shipbob) | To do |  |  | med | Yes |  | NEW in v2
Cyclone | Listing creation | Catalog | Product data filed → marketing brief | To do |  |  | med | No
Cyclone | Listing creation | Catalog | Brand language confirmed ◆ | To do |  |  | high | No
Cyclone | Listing creation | Design | Listing imagery / A+ uploaded | To do |  |  | med | No
Cyclone | Live | Catalog | Listings published live (Amazon + Shopify) | To do |  |  | med | Yes
Cyclone | Live | Logistics | Inventory received (Amazon + Shipbob) | To do |  |  | med | No |  | NEW in v2
Cyclone | Live | Marketing | Marketing brief finalized & ready | To do |  |  | med | Yes
Cyclone | Marketing | Marketing | KOL / influencer projects live | To do |  |  | med | No
Cyclone | Marketing | Social | Channel posts live (IG/YouTube/TikTok) | To do |  |  | med | No
Cyclone | Marketing | Ads | Launch ads running | To do |  |  | med | Yes
Cyclone | Marketing | Email | Launch email sequence sent | To do |  |  | med | No
Zephyr | Concept | Product | Form (intake) | Done |  |  | med | No
Zephyr | Concept | Product | Market research | Done |  |  | med | No
Zephyr | Concept | Product | Concept definition | Done |  |  | med | No
Zephyr | Concept | Product | Ben concept sign-off ◆ | Done |  |  | high | No
Zephyr | Build | Product | Prototype 1-2-3 approved | Done |  |  | med | Yes
Zephyr | Build | Product | Ben validation ◆ | Done |  |  | high | No
Zephyr | Build | Product | Costing & profit signed off | Done |  |  | med | No
Zephyr | Build | Design | Packaging / insert / manual locked | Done |  |  | med | No
Zephyr | Build | Design | Model name set | Done |  |  | med | No
Zephyr | Production | Product | Design freeze | Done |  |  | med | No
Zephyr | Production | Marketing | Marketing brief rough draft | Done |  |  | med | No |  | NEW in v2
Zephyr | Production | Product | Department requirements collected | Done |  |  | med | No |  | NEW in v2
Zephyr | Production | Product | Pre-production sample approved + BOM | Done |  |  | med | Yes
Zephyr | Production | Product | Mass production complete | Done |  |  | med | Yes
Zephyr | Production | Logistics | Dispatch details & tracking filed | Done |  |  | med | No |  | NEW in v2
Zephyr | Production | Logistics | Freight booked (sea + air samples) | Done |  |  | med | No
Zephyr | Content | Content | Hero / lifestyle shoot done | Done |  |  | med | Yes
Zephyr | Content | Content | Post-production done | Done |  |  | med | No
Zephyr | Content | Content | Content exported (instr/lifestyle/social/ads) | Done |  |  | med | Yes
Zephyr | Content | Design | A+ / infographic assets ready | Done |  |  | med | Yes
Zephyr | Listing creation | Catalog | Amazon SKU created | Done |  |  | med | Yes
Zephyr | Listing creation | Catalog | Shopify SKU created | Done |  |  | med | Yes
Zephyr | Listing creation | Catalog | Shipbob SKU created | Done |  |  | med | Yes |  | NEW in v2
Zephyr | Listing creation | Catalog | Next Smart Ship SKU created | Done |  |  | med | Yes |  | NEW in v2
Zephyr | Listing creation | Catalog | All ASINs sheet updated | Done |  |  | med | Yes |  | NEW in v2
Zephyr | Listing creation | Catalog | Shopify COGS sheet updated | Done |  |  | med | Yes |  | NEW in v2
Zephyr | Listing creation | Logistics | Shipping labels created (Amazon + Shipbob) | Done |  |  | med | Yes |  | NEW in v2
Zephyr | Listing creation | Catalog | Product data filed → marketing brief | Done |  |  | med | No
Zephyr | Listing creation | Catalog | Brand language confirmed ◆ | Done |  |  | high | No
Zephyr | Listing creation | Design | Listing imagery / A+ uploaded | Done |  |  | med | No
Zephyr | Live | Catalog | Listings published live (Amazon + Shopify) | Done |  |  | med | Yes
Zephyr | Live | Logistics | Inventory received (Amazon + Shipbob) | Done |  |  | med | No |  | NEW in v2
Zephyr | Live | Marketing | Marketing brief finalized & ready | Done |  |  | med | Yes
Zephyr | Marketing | Marketing | KOL / influencer projects live | Done |  |  | med | No
Zephyr | Marketing | Social | Channel posts live (IG/YouTube/TikTok) | Done |  |  | med | No
Zephyr | Marketing | Ads | Launch ads running | Done |  |  | med | Yes
Zephyr | Marketing | Email | Launch email sequence sent | Done |  |  | med | No
|  |  | Done |  | In progress |  | Blocked |  | Waiting on Ben
|  |  | 62 |  | 1 |  | 1 |  | 1

## 3. People
PEOPLE
Department | What this team owns | Head | Members | Deputy | Slack channel
Product | Intake, research, concept, prototyping, costing, design freeze, dept-requirements round-up, pre-prod sample + BOM, mass production |  |  |  | #team-product
Design | Packaging/insert/manual, model name, A+/infographics, listing imagery |  |  |  | #team-design
Catalog | Competitor analysis; SKUs: Amazon, Shopify, Shipbob, Next Smart Ship; All-ASINs, Ops & COGS sheets; data filing; listings go-live |  |  |  | #team-catalog
Content | Pre-production, hero/lifestyle shoot, post-production, content export (now incl. ad creatives) |  |  |  | #team-content
Social | IG / YouTube / TikTok posts |  |  |  | #team-social
Marketing | Brief: rough draft at design freeze → v1 → v2; KOL engine (MOAT·ASMR·Cinematic·Authority·Reach·Seed·UGC·Pro) |  |  |  | #team-marketing
Ads | Ad post-production, partnerships approval, paid campaigns |  |  |  | #team-ads
Email | Launch & campaign sequences |  |  |  | #team-email
CRM | Influencer DM → email pipeline |  |  |  | #team-crm
Logistics | Master order sheet, logistics planning & sheet, dispatch + tracking, freight, shipping labels (Amazon/Shipbob), carriers → USA, inventory receiving |  |  |  | #team-logistics
Ben (CEO) | ◆ gates: concept sign-off, prototype validation, brand language | Ben | — | (delegate?) | #bv-portfolio

## 4. Push rules
PUSH & HAND-OFF RULES — v2
# | Stage → Next | Planned days | Exit criteria (ALL ✓) | Mandatory depts | Push allowed by | Ben ◆ | Notify on push | SLA
1 | Concept → Build | 21 | Intake form · market research · concept definition (FINAL doc) · Ben sign-off ◆ | Product | DRI / Product head / Ben | Yes | Product, Design | 48h
2 | Build → Production | 35 | Prototype 1-2-3 · Ben validation ◆ · costing · packaging/insert/manual · model name | Product, Design | DRI / mandatory head / Ben | Yes | Product, Marketing, Logistics | 48h
3 | Production → Content | 45 | Design freeze · marketing brief ROUGH DRAFT (NEW) · dept requirements (NEW) · pre-prod sample + BOM (one to Taiwan, one to Ben) · mass production · dispatch details & tracking (NEW) · freight booked | Product, Marketing, Logistics | DRI / mandatory head / Ben | No | Content, Design | —
4 | Content → Listing creation | 21 | Shoot · post-production · content export incl. ADS (NEW) · A+/infographic assets | Content, Design | DRI / mandatory head / Ben | No | Catalog, Design, Logistics | —
5 | Listing creation → Live | 14 | Amazon + Shopify + Shipbob (NEW) + Next Smart Ship (NEW) SKUs · All-ASINs sheet (NEW) · COGS sheet (NEW) · shipping labels (NEW) · data filed → brief · brand language ◆ · imagery uploaded | Catalog, Design, Logistics | DRI / mandatory head / Ben | Yes | Catalog, Marketing, Logistics | 48h
6 | Live → Marketing | 10 | Listings live · inventory received Amazon + Shipbob (NEW) · marketing brief v1 finalized | Catalog, Logistics, Marketing | DRI / mandatory head / Ben | No | Marketing, Social, Ads, Email | —
7 | Marketing (final) | 30 | Brief v2 · KOL projects live (incl. Project Pro NEW) · channel posts · ads · email sequence | Marketing, Social, Ads | DRI / mandatory head / Ben | No | — complete 🎉 | —
Rows 3,5,6 changed in v2 — confirm planned days still hold with the heavier Listing/Live gates.

## 5. Contingencies
CONTINGENCIES
Scope | Risk | L | I | Score | Trigger | Fallback plan | Owner | Status
Apex | Factory holiday shutdown mid-July | 2 | 3 | 6 | PO not placed by Jun 20 | Place PO before Jun 20; alternate factory slot reserved | Product | Open
Apex | Ben validation delayed past SLA | 3 | 2 | 6 | ◆ waiting > 2 days | Auto-escalate; decision windows; delegate non-strategic after 4d | CEO | Open
Cyclone | Font license rejected → A+ redesign | 2 | 2 | 4 | Legal verdict Friday | Pre-approved alternative fonts; swap <1 day | Design | Open
Any | Sea freight delayed > 2 weeks | 2 | 3 | 6 | Carrier ETA slips twice | Air-freight launch subset; parallelize content/listing | Logistics | Watching
Any | Shipbob / Next Smart Ship receiving delays (NEW v2) | 2 | 2 | 4 | Receiving not confirmed 5d after delivery | Escalate with 3PL; Amazon-first stock split; hold Shopify launch date | Logistics | Watching
Any | Reshoot needed after review | 2 | 2 | 4 | Selects rejected | 1-week buffer before Listing; studio retainer 48h | Content | Watching
Any | Amazon listing suppressed at go-live | 1 | 3 | 3 | Flagged in Seller Central | Shopify-first; appeal in parallel | Catalog | Watching
Black Friday | Stock arrives after campaign start | 2 | 3 | 6 | Arrival < 7d before BF | Presale/backorder; 'ships by' ad messaging | Marketing + Logistics | Open
Any | DRI unavailable | 1 | 2 | 2 | Out > 3 working days | Deputy assumes DRI authority | Director | Watching

## 6. Rules
OPERATING RULES — confirm each
# | Rule | Why | Enforced by | Confirm (Y/N) | Notes
1 | Intake Form first | Nothing unlocks until the intake Form is done | Tracker
2 | Lane order | Department steps unlock sequentially per the flow chart | Tracker
3 | Stage gates | Push only when ALL exit criteria ✓ | Tracker
4 | Push rights | DRI / mandatory department head / Ben only | Tracker
5 | ◆ = Ben, 48h SLA | Breach auto-escalates | Tracker + Autopilot
6 | Evidence before ✓ | Flagged tasks need a link (now incl. Shipbob/COGS/labels) | Tracker
7 | Marketing brief starts early (NEW v2) | Rough draft due at design freeze, v1 at Live, v2 after listing | Gate map
8 | Logistics gates Production & Live (NEW v2) | Dispatch/tracking + labels + inventory receiving are blocking | Gate map
9 | Weekly check-in | DRI posts progress/blockers/asks weekly | Autopilot nudge
10 | Digests, not firehose | Daily/weekly digests + targeted alerts only | Slack bot (Ph.2)
11 | Tracker = state, Drive = docs | Link, never duplicate | Convention
12 | WIP limit 4 | Finish before starting | Director lens
13 | Date changes need a reason | Logged in check-in | Tracker
14 | Pre-mortem & retro | Risk at every push; retro at completion | Ritual
15 | Blocked > 3d escalates | To Director | Autopilot
16 | DRI authority | Only strategic forks go to Ben | Convention