## READ ME
BLACK VOYAGE — Task Playbook
How each department defines, updates, and pushes its tasks in the tracker
What this is | One tab per department. Each row becomes a task template in the tracker. Fill it in (or correct the pre-filled rows) so the tracker knows exactly how YOUR team works.
Task name | Short, action-phrased. This is the checkbox label everyone sees.
Definition of done | The one line that ends arguments. A task may only be checked ✓ when this sentence is true.
Evidence required | What link must be attached before the task can be checked (Drive doc, Loom, listing URL…). 'None' = no link needed.
Who updates | Role that owns flipping the status (to-do → in progress → done / blocked). 'Ben only' = ◆ decision gate.
Default urgency | low / med / high / urgent — pre-set on every new card.
Est. days | Your honest estimate. Feeds the timeline plan and delay alerts. You own this number.
Depends on | Task that must be done before this one can start (sequential unlock).
How to update a task | Open the card → click the checkbox to cycle status → attach the evidence link → add a note or Loom if context is needed.
How a card is pushed | When every department's gate tasks for the stage are ✓, the DRI or a mandatory department head presses Push. ◆ items need Ben.
Adding new rows | Add rows freely — new tasks appear in your department lane after review. Don't delete rows; strike through and note why.

## Gate rules
Stage → next | Mandatory departments | Ben gate ◆? | Who can push | Exit = all gate tasks ✓ in:
Concept → Build | Product | Yes | DRI / Product head / Ben | Product (+ Catalog contributes)
Build → Production | Product, Design | Yes | DRI / Product or Design head / Ben | Product, Design
Production → Content | Product, Logistics | No | DRI / Product or Logistics head / Ben | Product, Logistics
Content → Listing creation | Content, Design | No | DRI / Content or Design head / Ben | Content, Design
Listing creation → Live | Catalog, Design | Yes | DRI / Catalog or Design head / Ben | Catalog, Design
Live → Marketing | Catalog, Marketing | No | DRI / Catalog or Marketing head / Ben | Catalog, Marketing
Marketing (final) | Marketing, Social, Ads | No | DRI / any mandatory head / Ben | Marketing, Social, Ads, Email

## Product
Product — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Concept | Form (intake) | Intake form complete: why, spec, look, material, hardware, customer, price, date | Drive doc | Product lead | high | 3
Concept | Market research | Competitor set + product strengths documented; Apify pull attached | Sheet/report | Analyst | med | 7 | Form (intake)
Concept | Concept definition | Concept definition written & brainstorm meeting held; Figma updated | Figma | Product lead | med | 7 | Market research
Concept | Ben concept sign-off ◆ | Ben has approved the concept (decision logged on card) | None | Ben only | urgent | 2 | Concept definition
Build | Prototype 1-2-3 approved | Final prototype iteration accepted by team; QC notes attached | Photo/QC report | Product lead | high | 21 | Ben concept sign-off ◆
Build | Ben validation ◆ | Ben validated the prototype (decision logged) | Loom video | Ben only | urgent | 2 | Prototype 1-2-3 approved
Build | Costing & profit signed off | Costing sheet + margin target approved | Sheet/report | Product lead | high | 5 | Prototype 1-2-3 approved
Production | Design freeze | No further changes accepted; freeze announced to all departments | None | Product lead | high | 1 | Ben validation ◆
Production | Pre-production sample approved + BOM | Two samples: factory keeps one, one shipped to US; BOM filed | Photo/QC report | Product lead | high | 14 | Design freeze
Production | Mass production complete | Factory confirms completion; QC report attached | Photo/QC report | Product lead | med | 30 | Pre-production sample approved + BOM
Production | Department requirements collected | Every department's sample/photo/data needs gathered before dispatch | Sheet/report | Product lead | med | 3 | Packaging / insert / manual locked | NEW in v2
Total est. days (this dept):

## Design
Design — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Build | Packaging / insert / manual locked | Dielines final, print-ready files in Drive | Drive folder | Designer | high | 10 | Prototype 1-2-3 approved
Build | Model name set | Name confirmed with Ben; brand check done | None | Design lead | med | 3
Content | A+ / infographic assets ready | All A+ modules + infographics exported to spec | Drive folder | Designer | high | 7 | Content exported
Listing creation | Listing imagery / A+ uploaded | Imagery live in Amazon/Shopify backends | Listing URL | Designer | med | 3 | A+ / infographic assets ready
Total est. days (this dept):

## Catalog
Catalog — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Concept | Competitor analysis | Competitor listings analyzed: pricing, reviews, keywords | Sheet/report | Analyst | med | 5
Listing creation | Amazon SKU created | SKU exists in Seller Central with core attributes | Listing URL | Catalog lead | high | 2
Listing creation | Shopify SKU created | SKU exists in Shopify with core attributes | Listing URL | Catalog lead | high | 2
Listing creation | Product data filed → marketing brief | Product page data filed for internal users; feeds brief | Drive doc | Catalog lead | high | 3 | Amazon SKU created
Listing creation | Brand language confirmed ◆ | Ben confirmed brand language for listings | None | Ben only | urgent | 2 | Product data filed → marketing brief
Live | Listings published live (Amazon + Shopify) | Both listings public and purchasable | Listing URL | Catalog lead | urgent | 1 | Brand language confirmed ◆
Listing creation | Shipbob SKU created | SKU exists in Shipbob | Listing URL | Catalog lead | high | 1 |  | NEW in v2
Listing creation | Next Smart Ship SKU created | SKU exists in Next Smart Ship | Listing URL | Catalog lead | high | 1 |  | NEW in v2
Listing creation | All ASINs sheet updated | All-ASINs sheet row added/updated | Sheet/report | Catalog lead | med | 1 | Amazon SKU created | NEW in v2
Listing creation | Shopify COGS sheet updated | COGS sheet updated with landed cost | Sheet/report | Catalog lead | med | 1 | Shopify SKU created | NEW in v2
Total est. days (this dept):

## Content
Content — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Content | Hero / lifestyle shoot done | Shoot complete; selects folder shared | Drive folder | Content lead | high | 7 | Pre-production sample approved + BOM
Content | Post-production done | Edits final; color/sound approved | Drive folder | Editor | high | 10 | Hero / lifestyle shoot done
Content | Content exported (instruction / lifestyle / social clips / ads) | All formats exported & filed by type — now INCLUDING ad creatives (v2) | Drive folder | Editor | med | 3 | Post-production done | UPDATED in v2
Total est. days (this dept):

## Social
Social — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Marketing | Channel posts live (IG / YouTube / TikTok) | Launch posts published on all three channels | Listing URL | Social lead | high | 3 | Content exported
Total est. days (this dept):

## Marketing
Marketing — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Live | Marketing brief finalized & ready | Brief v2 final — unblocks influencer outreach | Drive doc | Marketing lead | urgent | 5 | Product data filed → marketing brief
Marketing | KOL / influencer projects live | First KOL wave live (MOAT/ASMR/Cinematic/Authority/Reach/Seed/UGC) | Listing URL | Marketing lead | high | 21 | Marketing brief finalized & ready
Production | Marketing brief rough draft | Rough draft delivered at design freeze — guides content & listing prep | Drive doc | Marketing lead | high | 5 | Design freeze | NEW in v2
Total est. days (this dept):

## Ads
Ads — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Marketing | Launch ads running | Launch campaigns active; links to campaigns | Listing URL | Ads lead | high | 5 | Marketing brief finalized & ready
Total est. days (this dept):

## Email
Email — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Marketing | Launch email sequence sent | Full launch sequence delivered to list | Sheet/report | Email lead | med | 5 | Marketing brief finalized & ready
Total est. days (this dept):

## CRM
CRM — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Marketing | Influencer DM routing live | Inbound DMs → email pipeline documented & running | None | CRM lead | med | 5
Total est. days (this dept):

## Logistics
Logistics — task playbook (edit freely; add rows at the bottom)
Stage | Task name | Definition of done | Evidence required | Who updates | Default urgency | Est. days | Depends on | Notes for tracker
Production | Freight booked (sea + air samples) | Sea bulk + air samples booked; tracking on card | Sheet/report | Logistics lead | high | 5 | Mass production complete
Production | Dispatch details & tracking filed | Sample dispatch details + tracking numbers filed on the card | Sheet/report | Logistics lead | med | 2 | Department requirements collected | NEW in v2
Production | Update master order sheet / logistics planning | Master order sheet + logistics sheet current for this launch | Sheet/report | Logistics lead | med | 2 |  | NEW in v2
Listing creation | Shipping labels created (Amazon + Shipbob) | Labels created and delivered to manufacturer; carriers arranged → USA | Sheet/report | Logistics lead | high | 3 | Mass production complete | NEW in v2
Live | Inventory received (Amazon + Shipbob) | Receiving confirmed at both warehouses | Sheet/report | Logistics lead | high | 5 | Shipping labels created (Amazon + Shipbob) | NEW in v2
Total est. days (this dept):